## Slide 1: The Importance of Solar Car Project Management
13 January 2018

## Slide 2
“All things are created twice; first mentally; then physically. The key to creativity is to begin with the end in mind, with a vision and a blueprint of the desired result.” — Stephen Covey

## Slide 3: Solar Car Projects are complex…
Involves multidisciplinary teams (mechanical, electrical, power, business)
  How do these teams work together?
Takes a long time
  How do you ensure that the project is done on time?
Requires development of new skills
  How do you know whether teaching resources are appropriately allocated?

## Slide 4: Project Management helps…
Break up the complicated into simpler pieces
Develop the roadmap for how to get there from here
Flesh out dependencies between teams
  “Just-in-time” manufacturing
Set trip-points for evaluation
  Am I getting done what I need to get done in time?
Prioritize work on a week-by-week basis
  Do work on the critical path

## Slide 5: How do I manage a project I’ve never done before?
Solar Car Challenge provides Project Planning Calendar
  September: Organize team, develop calendar, prepare presentations
  Early October: Preliminary design, budget, construction timeline
  Late October: Fundraising, purchasing plan
  November: Purchase parts
  December – March: Prototype & build
  April: Re-engineer car, as needed
  May – June: Test, test, test!
  July: Arrive at the race prepared!

## Slide 6: OK, how do I develop a construction timeline?
Break up project into major systems: mechanical, electrical, power, business
Then break each system into subsystems:
  Mechanical > Frame, Suspension, Steering, Brakes, Drivetrain
  Electrical > Propulsion (motor/controller), Auxiliary (instrumentation)
  Power > Batteries, Array
  Business > Fundraising, Community Events, etc.
Note dependencies between subsystems:
  Suspension must be completed before steering
  Batteries must be in place to power motor/controller
Break down into tasks based on solar car design and allocate time
  Attempt to finish by March to leave leeway for late tasks (critical chain)
  Be aggressive and finish early
  Don’t eat into your re-engineering/test time!

## Slide 7: Notional Schedule

## Slide 8: Break down tasks into individual “to-dos”, assign to team member
Example: Steering
  Determine location of steering wheel/column, rack-and-pinion
  Install front wheels
  Install rack-and-pinion
  Fabricate steering rods
  Fabricate mounts for steering column/wheel
Every task should be broken down into something achievable in a given workday
  Provides a sense of accomplishment
  Gives team members responsibility

## Slide 9: An example workday
Electric-Solar Powered Division Car
  Fabricate steering tie rods
  Fix rear suspension
  Install throttle pedal return spring
  Paint steering column and mount
  Install chain
  Mount instrument panel
Advanced Division Car
  Install front frame bulkhead
  Rivet in steering support angle
  Install steering column and wheel
  Make wiring schematic
  Run electrical conduit
  Install headrest
  Experiment with A/C charger
  Build access stairs

## Slide 10: In an ideal world… all tasks are accurately identified and finish on-time
Account for unplanned tasks
  When things get installed in the car, you might see conflicts/issues with preliminary design
  Revise schedule weekly with updated tasks (“living schedule”)
Account for delayed tasks
  Some tasks are more complicated than expected
  Plan for slippage!
Be aggressive in planning
  Tasks will never take less time than you planned!
  Challenge team members to complete tasks

## Slide 11: Summary
Project management provides method for assigning tasks and tracking progress
  Allow for reallocation of resources to keep project on schedule
Proper project management planning identifies dependencies and ensures that parts are available when needed
Be ready to modify schedule on a weekly basis to account for unexpected/unfinished tasks
Budget schedule for contingencies